## How to use
SEO Campaign Planner
Free template by Linksult ¦ linksult.com/seo-campaign-planner/
How to use this template
1. Set three to five goals in the Goals sheet, each with a baseline, a target and a deadline.
2. Plan the work in the Task plan by phase, with an owner and dates for each task.
3. Each month, record results in the Monthly results sheet.
4. Review progress monthly and adjust tasks based on what the numbers show.
Tips
• Make goals measurable: clicks, leads, rankings for named keywords or revenue from organic search.
• SEO usually takes months to show results, so plan the campaign for at least six months.
• Keep a note of changes such as new pages or Google updates so you can explain the numbers.
Rows shaded green are examples to show the format. Delete or overwrite them.
Want experts to do this for you? Request a free SEO quote at linksult.com/request-seo-quote/

## Goals
Goal | KPI | Baseline | Target | Current | Progress | Deadline | Owner | Notes
Grow organic leads | Form submissions from organic search (GA4) | 20 | 45 | 28 |  | 2027-04-30 | Sara | Monthly

## Task plan
Phase | Task | Owner | Start | End | Status | Notes
Research | Keyword research and competitor review | Ali | 2026-11-01 | 2026-11-14 | In progress
Technical | Fix crawl errors and speed issues from the audit | Dev team | 2026-11-10 | 2026-12-05 | Not started

## Monthly results
Month | Organic clicks (GSC) | Impressions (GSC) | Organic sessions (GA4) | Organic conversions | Keywords in top 10 | New referring domains | Notes
Nov 2026 | 1200 | 42000 | 1500 | 28 | 35 | 4 | Example row